## Cover
Client Name | Project Name |  | Date | Version Major | Version Minor
Internal Project | Mercury System |  | 17/07/2016 | 1 | 14
Description
Mercury System Hardware Open Poin List
Reference Documents |  |  | Version Major | Version Minor | Notes
Change Log
Author | Date | Version Major | Version Minor | Change
Francesco Ficili | 17/07/2016 | 1 | 0 | First Issue.
Francesco Ficili | 31/07/2016 | 1 | 1 | Added some issues on slave boards.
Francesco Ficili | 18/09/2016 | 1 | 2 | Added BB01_HW_006.
Francesco Ficili | 11/12/2016 | 1 | 3 | Solved Issues BB01_HW_003, BB01_HW_004, BB01_HW_005, SB01_HW_002, SB01_HW_003.
Francesco Ficili | 02/01/2017 | 1 | 4 | Solved all remaining issues for SB02, SB03, SB04, SB05.
Francesco Ficili | 03/01/2017 | 1 | 5 | Solved issues on EB01 and EB02.
Francesco Ficili | 09/01/2017 | 1 | 6 | Added SB310_HW_006, SB320_HW_006, SB340_HW_005. Updated OP tags to be aligned to new board names.
Francesco Ficili | 12/01/2017 | 1 | 7 | Added a sheet for SB130 and SB140.
Francesco Ficili | 22/02/2017 | 1 | 8 | Added and solved SB310_HW_007 and SB340_HW_006.
Francesco Ficili | 05/03/2017 | 1 | 9 | Added some issues .
Francesco Ficili | 12/03/2017 | 1 | 10 | Solved some hw issues.
Francesco Ficili | 04/01/2018 | 1 | 11 | Updated after some fixing on the second batch.
Francesco Ficili | 14/01/2018 | 1 | 12 | Updated again after some further analisys.
Francesco Ficili | 28/01/2018 | 1 | 13 | Some update on remaining boards.
Francesco Ficili | 10/02/2018 | 1 | 14 | Completed HW fixing on the whole board set.

## BB110
BB110 - Base Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Solution | Notes
BB110_HW_001 | Voltage Regulator | Wrong name of voltage regulator in BB01 BOM. | Design Issue | SOLVED | Modified BOM with right model. The regulator is a fixed range 3,3V.
BB110_HW_002 | Buttons | The button model used by the assembler is normally closed, while the suggested model is normally open. | Assembling Issue | SOLVED | The assembler has to use the suggested model or equivalent.
BB110_HW_003 | Capacitor C10 | When the modem type MB01 is plugged in, the modem case touch the upper side of C10. | Design Issue | SOLVED | Modify the HW project by changing C10 from metallic can case to SMD 0805 case (farnell code 1759428)
BB110_HW_004 | Battery connector polarity | The polarity of the battery connector has to be inverted | Concept Issue | SOLVED | Modify the HW project. This allows to be compliant with sparkfun lithium battery standard.
BB110_HW_005 | MSSP | Only on module of MSSP (Slave device and EEPROM must use the same bus). | Concept Issue | SOLVED | Modify the HW project. The EEP shall use the same bus as slave nodes, and 0x00 address will be reserved for data memory.
BB110_HW_006 | Modem Power Supply | The modem doesn't work fine with only the USB attached. It needs also the battery. There is probably a problem related with the quality of supply of battery charger. | Design Issue | SOLVED | The PROG resistor of MCP73831 was 10k, producing a max current of 100mA. Changed to 2k (500mA).
BB110_HW_007 | Reset button | Reset button is useless, it could be removed. | Improvement | SOLVED | To remove the reset button from the board design.
BB110_HW_008 | Charge status pin | Connect the charge status indicator to a uC pin. | Improvement | SOLVED | Modified PCB layout.
BB110_HW_009 | EEP power supply | Wrong connection of eep power supply | Design Issue | SOLVED | Rework PCB accordingly.
BB110_HW_010 | Wrong regulator | The assembler has placed a werong regulator on the board | Assembling Issue | NOT SOLVED | The assembler has to use the model indicated in the BOM, in particular MCP1825S-3302E/DB (3,3V fixed)
BB110_HW_011 | Line IO6-IO9 | Solder jumper should be placed to break Modem Mics and Spk instead of lines IO6-IO9 | Improvement | SOLVED | Rework PCB accordingly.
BB110_HW_012 | User LEDs | The User LEDs have been assebled reverted, so the LED does not light. | Assembling Issue | NOT SOLVED | The assembled has to verify the assembling polairyt of LEDs, we can provide a sample firmware to verify it if needed.
BB110_HW_013 | Low Power oscillator | Adda low power oscillator to enable the internal RTCC. | Improvement | NOT SOLVED | Must be still update the BOM.

## SB110
SB110 - Relay Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB110_HW_001 | Microcontroller package | The microcontroller package does not match with the footprint. | Design Issue | SOLVED | Modified HW project with the right footprint.
SB110_HW_002 | BJT package | The BJT package is wrong. | Design Issue | SOLVED | Need to be modified the HW project.
SB110_HW_003 | Resistive network | Resistive network could be removed, weak pull-ups present for any pin of device. | Improvement | SOLVED | Remove resistive network from layout.
SB110_HW_004 | Wrong header connector | The header connector to use must be stackable Arduino-like, male on bottom and female on top | Assembling Issue | SOLVED | Assembler must use correct P/N
SB110_HW_005 | Relay Connectors | Change JST connectors with MPT_0,5/3 | Improvement | SOLVED | Use of screwterminal connectors could improve usability of the board.
SB110_HW_006 | Relay Connectors 2 | Modify BOM and 3d according to SB110_HW_005. | Design Issue | SOLVED | Update BOM and 3d.
SB110_HW_007 | User LED | The User LED has been assebled reverted, so the LED does not light. | Assembling Issue | NOT SOLVED | The assembled has to verify the assembling polairyt of LEDs, we can provide a sample firmware to verify it if needed.
SB110_HW_008 | Relays | Replace relays | Improvement | SOLVED | Use futura sanyou model.

## SB130
SB 130 - Servo Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB130_HW_001 | Servo signal overcurrent | Overcurrent protection for servo control signal shall be introduced | Improvement | SOLVED | Rework PCB in order to introduce overcurrent protection.
SB130_HW_002 | Crystal | The crystal has not been mounted | Assembling Issue | NOT SOLVED | The assembler has to mount the crystal on this board.

## SB140
SB140 - HSD Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB140_HW_001 | PWM Outputs | PWM output should be used to control HSD. | Concept Issue | SOLVED | Reworked PCB in order to use PWM outputs for HSD control (CCP1-4 used for HSD control).
SB140_HW_002 | GND line | A GND line should be placed on the screw terminal connector. | Concept Issue | SOLVED | Modify PCB accordingly.

## SB310
SB310 - Ultrasonic Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB310_HW_001 | Microcontroller package | The microcontroller package does not match with the footprint. | Design Issue | SOLVED | Modified HW project with the right footprint.
SB310_HW_002 | Mercury connector | Pin Vddmcu and GND are inverted on mercury connector 10 pin (AppConn1) | Design Issue | SOLVED | Need to be modified the layout to correct the error
SB310_HW_003 | Resistive network | Resistive network could be removed, weak pull-ups present for any pin of device. | Improvement | SOLVED | Remove resistive network from layout.
SB310_HW_004 | Wrong header connector | The header connector to use must be stackable Arduino-like, male on bottom and female on top | Assembling Issue | SOLVED | Assembler must use correct P/N
SB310_HW_005 | Ultrasonic sensor | Ultrasonic sensor footprint is wrong | Design Issue | SOLVED | Correct footprint on layout
SB310_HW_006 | Interrupt line | Add a jumpered interrupt line connected to AppConn (Allow to implement more complex function in the SB) | Improvement | SOLVED | Updated PCB
SB310_HW_007 | Echo Pin | The echo pin should be connected to IC module input. | Design Issue | SOLVED | Updated schematic and PCB.
SB310_HW_008 | Crystal | A crystal shaould be added to be able to correctly use the IC module. | Concept Issue | SOLVED | The board must be redesigned using a PIC16F1829 and a crystal.
SB310_HW_009 | Ultrasonic RF power supply | The Ultrasonic sensor must be powered at 5v. The voltage from the BB is not enough so a charge pump must be added to the circuit. | Design Issue | SOLVED | Model LTC1516f and MAX682 can be suited for the scope.
SB310_HW_010 | Jumper | Jumper JP1 has been assembled wrongly. | Assembling Issue | NOT SOLVED | The assembler must use a male header.
SB310_HW_011 | Int pin transistor | Int pin transistor footprint is wrong. | Design Issue | SOLVED | Modify footprint accordingly.

## SB320
SB320 - Infrared Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB320_HW_001 | Microcontroller package | The microcontroller package does not match with the footprint. | Design Issue | SOLVED | Modified HW project with the right footprint.
SB320_HW_002 | Mercury connector | Pin Vddmcu and GND are inverted on mercury connector 10 pin (AppConn1) | Design Issue | SOLVED | Need to be modified the layout to correct the error
SB320_HW_003 | Resistive network | Resistive network could be removed, weak pull-ups present for any pin of device. | Improvement | SOLVED | Remove resistive network from layout.
SB320_HW_004 | Wrong header connector | The header connector to use must be stackable Arduino-like, male on bottom and female on top | Assembling Issue | SOLVED | Assembler must use correct P/N
SB320_HW_005 | Infrared sensors | Infrared sensor footprint is wrong | Design Issue | SOLVED | Correct footprint on layout.
SB320_HW_006 | Interrupt line | Add a jumpered interrupt line connected to AppConn (Allow to implement more complex function in the SB) | Improvement | SOLVED | Modified the PCB to implement the improvement.
SB320_HW_007 | PIR Sensor | The possiblity to use also a PIR sensor shuld be evaluated. In case the name of the board could change in Infrared/PIR Board | Improvement | SOLVED | Not possible to use PIR in this board. It is possible to foress a different board to support the sensor set similar to futura PIR sensor.
SB320_HW_008 | Jumper | Jumper JP1 has been assembled wrongly. | Assembling Issue | NOT SOLVED | The assembler must use a male header.
SB320_HW_008 | Int pin transistor | Int pin transistor footprint is wrong. | Design Issue | SOLVED | Modify footprint accordingly.

## SB330
SB330 - Temperature Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB330_HW_001 | Microcontroller package | The microcontroller package does not match with the footprint. | Design Issue | SOLVED | Modified HW project with the right footprint.
SB330_HW_002 | Mercury connector | Pin Vddmcu and GND are inverted on mercury connector 10 pin (AppConn1) | Design Issue | SOLVED | Need to be modified the layout to correct the error
SB330_HW_003 | Resistive network | Resistive network could be removed, weak pull-ups present for any pin of device. | Improvement | SOLVED | Remove resistive network from layout.
SB330_HW_004 | Wrong header connector | The header connector to use must be stackable Arduino-like, male on bottom and female on top | Assembling Issue | SOLVED | Assembler must use correct P/N
SB330_HW_005 | Interrupt line | Add a jumpered interrupt line connected to AppConn (Allow to implement more complex function in the SB) | Improvement | SOLVED | Modified the PCB to implement the improvement.
SB330_HW_006 | Com Pin | The signal pin should be connected to IC module input. | Design Issue | SOLVED | Updated schematic and PCB.
SB330_HW_007 | Crystal | A crystal should be added to be able to correctly use the IC module. | Concept Issue | SOLVED | The board must be redesigned using a PIC16F1829 and a crystal.
SB330_HW_008 | Temp sensor | Wrong orientation of Temp sensor | Design Issue | SOLVED | Modify PCD design
SB330_HW_009 | Transistor | Wrong transistor footprint | Design Issue | SOLVED | Modify PCD design

## SB120
SB 120 - Neopixel Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB120_HW_001 | Microcontroller package | The microcontroller package does not match with the footprint. | Design Issue | SOLVED | Modified HW project with the right footprint.
SB120_HW_002 | Mercury connector | Pin Vddmcu and GND are inverted on mercury connector 10 pin (AppConn1) | Design Issue | SOLVED | Need to be modified the layout to correct the error
SB120_HW_003 | Resistive network | Resistive network could be removed, weak pull-ups present for any pin of device. | Improvement | SOLVED | Remove resistive network from layout.
SB120_HW_004 | Wrong header connector | The header connector to use must be stackable Arduino-like, male on bottom and female on top | Assembling Issue | SOLVED | Assembler must use correct P/N
SB120_HW_005 | Crystal | A crystal should be added to be able to correctly use the IC module. | Concept Issue | SOLVED | The board must be redesigned using a PIC16F1829 and a crystal.
SB120_HW_006 | Power connector | Change to mini screwterminal | Improvement | SOLVED | As described.
SB120_HW_007 | Ch. Number | Upgrade to 3 channel | Improvement | SOLVED | As described.

## SB340
SB3340 - Accelerometer Board OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB340_HW_001 | Transistor | Wrong transistor footprint | Design Issue | SOLVED | Modify PCD design

## SB810
SB810 - Proto Board Slave A OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
SB810_HW_001 | UART Line | UART connection option must be inserted | Design Issue | SOLVED | Modify PCB to add UART connection.
SB810_HW_002 | Transistor | Wrong transistor footprint | Design Issue | SOLVED | Modify PCD design

## EB210
EB111 - Expansion Quad OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
EB210_HW_001 | I2C lines not connected. | I2C is not connected to mercury connector. | Design Issue | SOLVED | Modified PCB accordingly.
EB210_HW_002 | User LED | The User LED has been assebled reverted, so the LED does not light. | Assembling Issue | NOT SOLVED | The assembled has to verify the assembling polairyt of LEDs, we can provide a sample firmware to verify it if needed.
EB210_HW_003 | LCD power | Possible improvement: use a charge pump to power the LCD. This gives a better contrast even with battery and provide the possibility to shut the LCD off. | Improvement | SOLVED

## EB110
EB110 - Expansion Dual OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
EB110_HW_001 | Silkscreen on PicKit connector | The silkscreen for individual pin name is missing on pickit connector. | Improvement | SOLVED | Add the silkscreen.
EB110_HW_002 | CN5 and CN6 header | CN5 and CN6 header must be 90° to allow connection when mercury board are mounted over. | Assembling Issue | NOT SOLVED | Check BOM.
EB110_HW_003 | Expansion Board Cascading | Add two connectors to carry Vbat, Vdd, GND, SDA and SCL from one expansion board to another (cascade connection). | Improvement | SOLVED | Modified the PCB to implement the improvement.

## EB111
EB111 - Expansion Quad OPL
Issue ID | Short Name | Description | Issue Type | Status | Implemented Solution | Notes
EB111_HW_001 | Silkscreen on PicKit connector | The silkscreen for individual pin name is missing on pickit connector. | Improvement | SOLVED | Add the silkscreen
EB111_HW_002 | CN10 and CN9 header | CN10 and CN9 header must be 90° to allow connection when mercury board are mounted over. | Assembling Issue | NOT SOLVED | Check BOM
EB111_HW_003 | Expansion Board Cascading | Add two connectors to carry Vbat, Vdd, GND, SDA and SCL from one expansion board to another (cascade connection). | Improvement | SOLVED | Modified the PCB to implement the improvement.

## enums (hidden)
Status
NOT SOLVED
SOLVED
WORKING

## List
Issue Type
Design Issue
Assembling Issue
Concept Issue
Improvement